## Slide 1: SimpleRex – Progress Report 2
Grant Harmeyer – ITC 250
Fall 2017 – November 30, 2017
Dr. Paul I. Lin

## Slide 2: Project Summary
SimpleRex is a web-based application that provides management capabilities for IT service requests within an organization
Users have the ability to log in and submit a ticket. Additionally, users can check the status of their tickets
Technicians will be able to setup users, reset passwords and add comments to tickets when working to resolve the reported issues.

## Slide 3: Product Features
Service Request
  Ticket submission
  Ticket inquiry and notification
Notification
  Email system for notification of :
    Comment
    Ticket status change
Role-based access
  Technician
    User management
    Ticket management
  User
    Ticket submission
    Ticket inquiry

## Slide 4: Project Scope
Deployment
  Database deploy to production
  Website deploy to production (http://simplerex.harmeyer.me)
11/16/2017
  Scope Change
    Service catalog feature is no longer considered part of the minimally viable product
11/30/2017
  No change in scope from the last report.
Activities
  Database design
  Scaffolding of site
  Extend scaffold for Comments
  Branding and UX
Testing
  Login/Logout/Registration
  Roles (Technician, User)
  Email updates

## Slide 5: Project Timeline (11/30/2017)
Task Name | Duration | Work | % Complete
SimpleRex | 80 hrs | 35 hrs | 
Site scaffolding | 2 hrs | 2 hrs | 100%
Branding (Foundation) | 2 hrs | 2 hrs | 100%
Database Design | 1 hr | 1 hr | 100%
Module Implementation | 48 hrs | 22 hrs | 
Email System | 4 hrs | 4 hrs | 80%
Authentication and User Management | 6 hrs | 6 hrs | 100%
Service Catalog | 4 hrs | 4 hrs | 0%
Ticket Entry and Management | 8 hrs | 8 hrs | 95%
Minimally Viable Product | 0 hrs | 0 hrs | 
Testing | 32 hrs | 8 hrs | 
Authentication and User Management | 1 hr | 2 hrs | 100%
Service Catalog | 1 hr | 2 hrs | 0%
Email system | 1 hr | 2 hrs | 50%
Ticket Entry and Management | 1 hr | 2 hrs | 95%
Testing Complete | 0 hrs | 0 hrs | 
Final Delivery | 0 hrs | 0 hrs | 

## Slide 6: Problems and Corrections
11/16/2017
  Service Catalog was determined to not be necessary for this project at this time
  The email system should not be beyond the scope of the project, but is lower in priority and if time is not available, it will be removed from the minimally viable product.
11/30/2017
  Emailing from the system proved to be a bit challenging, but it has been largely implemented as designed
  Branding was updated and color scheme/styling updated.

## Slide 7: System Software and Tools
Tools
  Visual Studio Code
  FileZilla FTP Client
  MySQL Workbench
Hosting
  Microsoft Azure
    App Service for web application
    PaaS database service for MySQL database
    http://simplerex.harmeyer.me
User Interface
  HTML5
  Bootstrap (Responsive)
  JavaScript
    Client-side validation and logic
Application Logic
  PHP
    Cake PHP (https://cakephp.org)
    MVC scaffold
      View extension for Comments
  MySQL for database

## Slide 8: User Interface 11/16/2017
User Management
Login Register

## Slide 9: User Interface 11/30/2017 (Logged in as a technician)

## Slide 10: User Interface 11/30/2017 (Logged in as a user)