## Sheet1
Main Tasks
Schedule | Time
Design main web page (Home screen) | 1 week
Design available services web page | 2 weeks
Design existing customer login page | 1 week
Design new customer creation page | 1 week
Project report & presentation slides | 1 week
Sub Tasks (Main Page)
Schedule | Time
Design the layout and color scheme | 2 days
Design links to other pages | 2 days
Design an "About Us" page | 2 days
Buffer time | 1 day
Sub Tasks (Available Services Page)
Schedule | Time
Create a list of available services | 1 day
Design an interactive list of services | 5 days
Buffer time | 1 day
Sub Tasks (Existing Customer Page)
Schedule | Time
Design GUI for existing customer login | 2 days
Design the login code for GUI | 5 days
Sub Tasks (New Customer Page)
Schedule | Time
Design GUI for new customer creation | 2 days
Implement server side code to receive information | 5 days